## GANTT DIAGRAM HMS
TASK | START DATE | END DATE | Responsable | state | 2021-09-29 | 2021-09-30 | 2021-10-01 | 2021-10-04 | 2021-10-05 | 2021-10-06 | 2021-10-07 | 2021-10-08 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14 | 2021-10-15 | 2021-10-18 | 2021-10-19 | 2021-10-20 | 2021-10-21 | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28 | 2021-10-29 | 2021-10-30 | 2021-10-31 | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04 | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08
SPRING 1 | 29/09/2021 | 11/10/2021
Database | 29/09/2021 | 30/09/2021 | Rafiki, Cielo, Katheren, Juan, Margarita, Imed, Shameer | Closed
Home | 29/09/2021 | 30/09/2021 | Younnes, Ouisal | Closed
Register | 01/10/2021 | 04/10/2021 | Shammer, Younnes, Dilpret | Closed
My Profile | 05/10/2021 | 05/10/2021 | Imed, Margarita, Khatereh, Delnia | In progress
Login | 05/10/2021 | 07/10/2021 | Shammer, Younnes, Dilpret | Open
Create an appoinment | 07/10/2021 | 11/10/2021 | Imed, Ouisal, Juan, Cielo, Delnia | Open
Appoinment Details | 07/10/2021 | 11/10/2021 | Yassine, Younnes | Open
Patient list | 07/10/2021 | 11/10/2021 | Shammer, Margarita, Khatereh, Cielo, Rafiki | Open
SPRING 2 | 12/10/2021 | 25/10/2021
My transaccion history
Create prescription
Create patient record
SPRING 3 | 26/10/2021 | 08/11/2021
Payment
Testing

## SPRING 1
SPRING 1
Task | Front | Back | Test | Level
Login | Shameer | Shameer | Youness - dilpreth | high
Register | Shameer | Shameer | Youness - dilpreth | Low
Home | Younees | Younees | Ouisal | High
My Profile patient/doctor/nurse | Imed | Margarita Khatereh | Delnia | Low
Create appoinment | Imed - Ouisal | Juan - Cielo | Delnia | High
My Appoinment and Appointment details | Yassine | Youness | Yassine -Youness | High
Patient list | Shameer | Cielo –Margarita- Khatereh | Rafiki | Low
Back up –Restore, emergency disaster recovery | Isaq | Isaq | Isaq | High

## SPRING 2
SPRING 2
Task | Front | Back | Test | Level
My transaccion history
Create prescription
Create patient record
Back up –Restore, emergency disaster recovery

## SPRING 3
SPRING 2
Task | Front | Back | Test | Level
Payment
Testing